## Contribs
SHORT DOC NB | SHORTNAME | SOURCE | STATUS | DOC TYPE | Release | TS/TR
SDS-2022-0020 | Discussion_on_announcement_issues | Deutsche Telekom, ETSI | Draft | New feature | R5 | TS-0001
SDS-2023-0033R05 | clarification of the behavior of flexContainerInstance in TS-0004 | Sejong University | Draft | Change | R4 | TS-0004 | Revised
SDS-2023-0096R01 | Set “creator” attribute to request originator in notifications (TS-0004) | Andreas Kraft (DT), Andreas Neubacher (DT), Miguel Angel Reina Ortega (ETSI) | Noted | Change | R5 | TS-0004 | Revised
SDS-2023-0098R01 | TS-0001 subsciption multipleRecipients and repeatedNotifications | SyncTechno Inc. | Noted | New Feature | R5 | TS-0001 | Replaced by 134/135
SDS-2023-0134R01 | TS-0001 notificationURI target format clarification | SyncTechno Inc. | Draft | Change | R5 | TS-0001
SDS-2023-0135 | TS-0001 subsciption repeatedNotifications | SyncTechno Inc. | Draft | New feature | R5 | TS-0001
SDS-2023-0099 | TS-0001 subscription location based notifications | SyncTechno Inc. | Draft | New Feature | R5 | TS-0001
SDS-2023-0100 | TS-0001 mqtt multicastCapability | SyncTechno Inc. | Draft | New Feature | R5 | TS-0001
SDS-2023-0101 | Discussion paper for request prioritization | SyncTechno Inc. | Draft | Discussion | R5
SDS-2023-0102 | TS-0001 Priority request primitive | SyncTechno Inc. | Draft | New Feature | R5 | TS-0001
SDS-2023-0103 | Discussion paper on new updateMethod attribute for flexContainer | SyncTechno Inc. | Draft | Discussion | R5
SDS-2023-0104 | TS-0001 flexContainer updateMethod attribute | SyncTechno Inc. | Draft | New Feature | R5 | TS-0001
SDS-2023-0105 | use cases of No-response option - CoAP | Abhijan Bhattacharyya, TCS | Noted | New Feature | R5 | TS-0008
SDS-2023-0115 | TS-0004 fixing polygon data format | KETI | Withdrawn | Change |  | TS-0004
SDS-2023-0118R01 | adding location attribute to contentInstance (TS-0001 R5) | KETI | Draft | New Feature | R5 | TS-0001 | Revised
SDS-2023-0114R01 | adding location attribute to contentInstance | KETI | Draft | New Feature | R4 | TS-0001 | Revised
SDS-2023-0130 | adding location attribute to contentInstance (R5) | KETI | Draft | New feature | R5 | TS-0004
SDS-2023-0119 | discussion on AI/ML model management interfaces | KETI | Noted | Discussion
SDS-2023-0122 | retrieving multiple oldest and latest contentInstances (TS-0001 R5) | KETI | Draft | New Feature | R5 | TS-0001
SDS-2023-0123 | retrieving multiple oldest and latest contentInstances (TS-0001 R4) | KETI | Draft | New Feature | R4 | TS-0001
SDS-2023-0124 | retrieving multiple oldest and latest contentInstances (TS-0001 R3) | KETI | Draft | New Feature | R3 | TS-0001
SDS-2023-0125 | TS-0004_AnnouncementClarifications_R4 | Miguel Angel Reina Ortega (ETSI), Andreas Kraft (DT), Bob Flynn (Exacta) | Draft | Change | R4 | TS-0004
SDS-2023-0137 | Make missingDataCurrentNr in TimeSeries mandatory (TS-0001) (R2) | Andreas Kraft (DT), Andreas Neubacher (DT), Miguel Angel Reina Ortega (ETSI) | Draft | Change | R2 | TS-0001
SDS-2023-0138 | Make missingDataCurrentNr in TimeSeries mandatory (TS-0001) (R3) | Andreas Kraft (DT), Andreas Neubacher (DT), Miguel Angel | Draft | Change | R3 | TS-0001
SDS-2023-0139 | Make missingDataCurrentNr in TimeSeries mandatory (TS-0001) (R4) | Andreas Kraft (DT), Andreas Neubacher (DT), Miguel Angel Reina Ortega (ETSI) | Draft | Change | R4 | TS-0001
SDS-2023-0086R01 | New event evaluation mode for crossResourceSubscription – TS-0001 | Andreas Kraft (DT), Andreas Neubacher (DT), Bob Flynn (Exacta GSS) | Draft | New feature | R5 | TS-0001 | Revised
SDS-2023-0087R01 | New event evaluation mode for crossResourceSubscription – TS-0004 | Andreas Kraft (DT), Andreas Neubacher (DT), Bob Flynn (Exacta GSS) | Draft | New feature | R5 | TS-0004 | Revised
SDS-2022-0173R02 | CSEResourceIDInterfaceCorrection_R4 | C-DOT | Draft | Change | R4 | TS-0001 | Revised
SDS-2022-0177R01 | Referencing Subscriptions | DT, Orange, Exacta GSS, CDOT | Draft | Discussion |  |  | Revised
SDS-2022-0182 | expirationTimeHandilinginSSP | C-DOT | Draft | Change | R4 | TS-0001 | Not opened yet
SDS-2022-0189R03 | expirationTime_Create_Update_Handling_R4 | C-DOT | Draft | Change | R4 | TS-0004 | Revised
SDS-2023-0022R01 | TS-0004_XSD_rules_R4 | Miguel Angel Reina Ortega (ETSI), Andreas Kraft (DT) | Draft | Change | R4 | TS-0004 | Revised
SDS-2023-0028 | TS-0022_XSD_namespaces_R4 | Miguel Angel Reina Ortega (ETSI), Andreas Kraft (DT) | Draft | Change | R4 | TS-0022 | Not opened yet
SDS-2023-0079 | TS-0008 Introduce no-response option | Abhijan Bhattacharyya, TCS | Noted | Change | R5 | TS-0008 | Additional CRs expected
SDS-2022-0174 | CSEResourceIDInterfaceCorrection_R3 | C-DOT | Draft | Change | R3 | TS-0001 | Revision expected
SDS-2022-0175 | CSEResourceIDInterfaceCorrection_R2 | C-DOT | Draft | Change | R2 | TS-0001 | Revision expected
SDS-2022-0183R01 | TS-0001 - Another correction for the notificationStatsInfo and notificationStatsEnable | Andreas Kraft, Andreas Neubacher (Deutsche Telekom), Miguel Angel Reina Ortega (ETSI) | Draft | Change | R4 | TS-0001 | Revision expected
SDS-2022-0184R01 | TS-0004 - Another correction for the notificationStatsInfo and notificationStatsEnable attributes | Andreas Kraft, Andreas Neubacher (Deutsche Telekom), Miguel Angel Reina Ortega (ETSI) | Draft | Change | R4 | TS-0004 | Revision expected
SDS-2022-0190 | TS-0004_notificationContentType_R4 | Miguel Angel Reina Ortega (ETSI), Andreas Kraft (DT) | Noted | Change | R4 | TS-0004 | To be revisited
SDS-2022-0204 | Adding time retrieval method for constrained devices | Andreas Kraft, Andreas Neubacher (DT), Miguel Angel Reina Ortega (ETSI), Bob Flynn (Exacta GSS) | Draft | Change | R5 | TS-0001
SDS-2022-0205 | Access Control for Subscription Notifications | Andreas Kraft, Andreas Neubacher (DT), Miguel Angel Reina Ortega (ETSI), Bob Flynn (Exacta GSS) | Draft | Change |  | TS-0001
SDS-2022-0206 | fcinEnabled attribute to control flexContainerInstance R5 | Sejong Univ., Deutsche Telekom, Exactagss, Orange, EGM | Draft | Change | R5 | TS-0001
SDS-2022-0014R02 | Improving Queries in Discovery and Retrieve Requests | Deutsche Telekom | Noted | Discussion | R5 | TS-0001
SDS-2022-0110R04 | Automatic_recognition_of_identification_schemes_for_heterogeneous_IoT_identifiers | CMCC | Noted | New feature | R5 | TR-0033
SDS-2022-0124 | subjectAltName_AuthenticationProfile | C-DOT | Noted | Change | R4 | TS-0022 | Revision expected
SDS-2022-0143R02 | TS-0001 mlDatasetPolicy resource | KETI | Draft | New feature | R5 | TS-0001
SDS-2022-0144 | TS-0004 mlDatasetPolicy procedures | keti | Draft | New feature | R5 | TS-0004
SDS-2022-0149 | Enhancing [dataCollection] mgmtObj Specialization | Deutsche Telekom, C-DOT,Exactagss, Orange | Draft | Change | R5 | TS-0022
SDS-2023-0091 | Discussion paper for enhancing Public Warning Service | SyncTechno Inc | Noted | Discussion | R5 | TS-0001, TS-0004
SDS-2022-0075 | Triggering Value Retrieval and Updates | Andreas Kraft, Andreas Neubacher (Deutsche Telekom), Bob Flynn (Exacta), Cyrille Bareau (Orange), Miguel Angel Reina Ortega (ETSI) | Draft | Discussion
SDS-2022-0015 | Add lastSeenTime and lastCommunicationTime attributes to <node> | Deutsche Telekom | Draft | New feature | R5 | TS-0001
ITU-T related
TP-2022-0032 | Updated Resolution table | Rana Kamill, BT | Noted | Notes | R2 | TS-0003
SDS-2022-0033 | Rel 2 Ref updates 1-TS-0003 | BT | Noted | Change | R2 | TS-0003 | May need revision - depends on ITU-T meeting
SDS-2022-0115R02 | Key_Storage | Rana Kamill, BT | Noted | Change | R2 | TS-0003 | Revision expected after Itu-T meeting
Other docs
SDS-2022-0002R01 | CMDH_Buffering | Exacta | Draft | Discussion | R5 | TS-0022 | Revised
SDS-2022-0008 | Improve TS-0001 clause 9.6.26.3 “Common Attributes for Announced Resources” | Deutsche Telekom | Noted | Change | R4 | TS-0001
SDS-2022-0036 | Introduction of new data types for Advanced Semantic Discovery | JK Consulting and Projects | Noted | New feature | R5 | TS-0004 | Revision expected
SDS-2022-0055 | Introduction_of_new_request_parameters_for_Advanced_Semantic_Discovery | JK Consulting and Projects | Noted | New feature | R5 | TS-0001 | Revision expected
SDS-2021-0259 | Key issue on Right to be Forgotten | Hyundai Motors, KETI | Draft | New feature | R5 | TR-0062
SDS-2021-0262R01 | gsma_reqts_001 | Exacta | Draft | New feature | R5 | TR-0063 | Not discussed
Agreed
Discussed
Needs Attention
Note on A77: Karen Hughes: Not discussed during SDS 52

## CR Packs
TS-0001 (R2) | TS-0001 (R3) | TS-0001 (R4) | TS-0001 (R5) | TS-0003 (R2) | TS-0003 (R3) | TS-0003 (R4) | TS-0004 (R2) | TS-0004 (R3) | TS-0004 (R4) | TS-0004 (R5) | TS-0005(R3) | TS-0006(R3) | TS-0008 (R2) | TS-0008 (R3) | TS-0008 (R4) | TS-0009 (R2) | TS-0009 (R3) | TS-0009 (R4) | TS-0010 (R2) | TS-0010 (R3) | TS-0010 (R4) | TS-0014 (R2) | TS-0014 (R3) | TS-0022 (R2) | TS-0022 (R3) | TS-0022 (R4) | TS-0022 (R5) | TS-0026 (R3) | TS-0026 (R4) | TS-0026 (R5) | TS-0032 (R2) | TS-0032 (R3) | TS-0033 (R5) | TS-0034 (R5)
[10 empty] | SDS-2021-0114R01 | [16 empty] | SDS-2021-0185R02 |  |  | SDS-2022-0185R04 |  |  | SDS-2022-0114R06 | SDS-2021-0217R03
SDS-2021-0190
SDS-2022-0006R01
SDS-2022-0062R02
SDS-2023-0064R01
SDS-2022-0186R04
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not included in release 5.0 baseline but are to be included in 5.1 baseline

## WI
WI | Title of WI | SDS39 | SDS40 | SDS41 | SDS42 | SDS43 | SDS44 | SDS45 | SDS46 | SDS47 | SDS48 | SDS49 | SDS50 | SDS51 | SDS52 | SDS53 | SDS54 | SDS55 | SDS56 | SDS57 | 58% | Comments
WI-0053 | Enhancements on Semantic Support | 30% | 40% | 50% | 75% | 90% | 95% | 97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0058 | Interworking with 3GPP networks | 60% | 68% | 75% | 80% | 80% | 90% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0072 | Modbus Interworking | 60% | 70% | 75% | 80% | 85% | 90% | 91% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0076 | Lightweight oneM2M Services | 20% | 40% | 50% | 60% | 65% | 70% | 80% | 85% | 90% | 93% | 97% | 97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0077 | Attribute based Access Control Policy | 65% | 75% | 75% | 80% | 85% | 85% | 90% | 92% | 93% | 95% | 97% | 97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0080 | Edge and Fog Computing | 20% | 35% | 45% | 55% | 65% | 70% | 80% | 85% | 90% | 95% | 97% | 97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0083 | oneM2M Service Subscribers and Users | 30% | 50% | 50% | 60% | 70% | 75% | 80% | 85% | 90% | 90% | 91% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0089 | Getting started with oneM2M | 20% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 25% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | R4/R5 work in progress
WI-0091 | oneM2M Services and Platform Discovery | 15% | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | Postponed to R5
WI-0093 | Action Triggering Enhancements | 5% | 20% | 20% | 30% | 40% | 60% | 80% | 80% | 85% | 90% | 91% | 93% | 93% | 97% | 97% | 97% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0090 | oneM2M and Zigbee interworking | 0% | 0% | 0% | 0% | 0% | 30% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | Rel-5 TR work in progress
WI-0095 | oneM2M System Enhancements to Support Data Protection Regulations | [5 empty] | 30% | 50% | 55% | 65% | 65% | 65% | 65% | 65% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | Rel-5 TR work in progress
WI-0096 | Effective IoT Communication to Protect 3GPP Networks | [20 empty] | Rel-5 TR work in progress | bar: SDS39 to 58%
WI-0100 | oneM2M and SensorThings API | [6 empty] | 5% | 5% | 15% | 20% | 20% | 20% | 25% | 25% | 40% | 50% | 50% | 50% | 55% | 70% | Rel-5 TR work in progress
WI-0101 | Advanced Semantic Discovery | SDS45: 5%; SDS46: 5%; SDS47: 15%; SDS56: 60%; SDS57: 60%; 58%: 60% | TS started
WI-0102 | System enhancements to support Data License Management | [7 empty] | 5% | 15% | 30% | 40% | 45% | 45% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | Rel-5 TR work in progress
WI-0105 | System enhancements to support AI capabilities | SDS55: 75%; SDS56: 80%; SDS57: 85%; 58%: 85% | Initial concepts discussed
WI-0109 | IPE-based_Device_Management_with_FlexContainers | 5% | 20% | 20% | 30% | 40% | 60% | 80% | 80% | 85% | 90% |  |  |  |  | 5% | 30% | 80% | 80% | 85% | 85% | Rel 5 TS
WI-0064 | Adaptation of oneM2M for Smart City | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | Postponed to R5
WI-0069 | Heterogen. identificat. service in oneM2M syst. | 50% | 50% | 60% | 60% | 60% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | Postponed to R5
S

## Open Issues
Issue ID | URL | Title | State | Notes | Author | Labels
4 | https://git.onem2m.org/issues/issues/-/issues/4 | Clarification needed for Subscriptions and expirationCounter | Open | CR needed | Andreas Kraft | TS-0001,TS-0004,clarification needed,discussion
6 | https://git.onem2m.org/issues/issues/-/issues/6 | Type of resourceID for NotificationContentType=3 (resourceID) | Open | CR needed | Andreas Kraft | TS-0004,clarification needed,discussion
12 | https://git.onem2m.org/issues/issues/-/issues/12 | Error conditions for subscription resource need updates in table 10.2.10.2-1 | Open |  | Bob Flynn | TS-0001,enhancement,fix needed
14 | https://git.onem2m.org/issues/issues/-/issues/14 | Missing XSD for TS-0022 FieldDevices | Open | XSD | Andreas Kraft | TS-0022,XSD
16 | https://git.onem2m.org/issues/issues/-/issues/16 | TS-0022 : shortnames missing for [wificlient] | Open | CR SDS-2020-0377R02 | Andreas Kraft | TS-0022,fix needed
17 | https://git.onem2m.org/issues/issues/-/issues/17 | TS-0022 : shortnames missing for [OAuth2Authentication] | Open | CR SDS-2020-0377R02 | Andreas Kraft | TS-0022,fix needed
18 | https://git.onem2m.org/issues/issues/-/issues/18 | TS-0001: Missing child resources (<mgmtObj> specializations) for <node> in Table 9.6.18-1 | Open |  | Andreas Kraft | TS-0001,TS-0022,fix needed
19 | https://git.onem2m.org/issues/issues/-/issues/19 | Discussion: Unanounced <mgmtObj> specializations in TS-0022 | Open | More investigation needed | Andreas Kraft | TS-0022,discussion
22 | https://git.onem2m.org/issues/issues/-/issues/22 | TS-0009 : wrong reference to definition of responseTypeInfo in TS-0004 | Open |  | Andreas Kraft | TS-0009,editorial
23 | https://git.onem2m.org/issues/issues/-/issues/23 | TS-0009 : wrong cardinality for Token Request Indicator in Table 6.2.2.2-1 | Open |  | Andreas Kraft | TS-0009,editorial
24 | https://git.onem2m.org/issues/issues/-/issues/24 | TS-0009, TS-0004 : Wrong spelling of "Authorization Signatures" request parameter | Open | Fix needed in TS-0009 | Andreas Kraft | TS-0009,editorial
26 | https://git.onem2m.org/issues/issues/-/issues/26 | TS-0009 : Missing mappings for "Group request Target Members", "Group Request Somecast Target Number", "Primitive Profile Identifier" | Open |  | Andreas Kraft | TS-0009,enhancement,fix needed
29 | https://git.onem2m.org/issues/issues/-/issues/29 | TS-0010 : Issues with the MQTT binding specification | Open |  | Andreas Kraft | TS-0010,clarification needed,discussion,editorial
32 | https://git.onem2m.org/issues/issues/-/issues/32 | TS-0001 and TS-0004: Notifying end-user regarding creation of <flexContainerInstance> resource not explicitly mentioned | Open | Discussion needed | Muhammad Hamza | TS-0001,TS-0004,discussion
33 | https://git.onem2m.org/issues/issues/-/issues/33 | Handling of niddRequired attribute in TS-0004 | Open | Awaiting update of TR-0063 | Poornima Shandilya | TS-0004,TS-0026
34 | https://git.onem2m.org/issues/issues/-/issues/34 | Missing Attributes in <AE> resource in TS-0004 | Open | CR needed | Poornima Shandilya | TS-0004
35 | https://git.onem2m.org/issues/issues/-/issues/35 | TS-0010, clause 6.6 URI Format: undefined behaviour | Open |  | Andreas Kraft | TS-0010
36 | https://git.onem2m.org/issues/issues/-/issues/36 | TS-0026 Error behavior missing when MT request size is greater than maxPacketSize | Open |  | Poornima Shandilya | TS-0026
37 | https://git.onem2m.org/issues/issues/-/issues/37 | TS-0009 - Character-set for http binding & json | Open |  | Andreas Kraft | TS-0009
38 | https://git.onem2m.org/issues/issues/-/issues/38 | Add paragraph on result content filtering to TS-0004 | Open | ready to close ? | Peter Niblett | TS-0004
43 | https://git.onem2m.org/issues/issues/-/issues/43 | TS-0004: Authorsigns element unclear | Open |  | Peter Niblett | TS-0004,clarification needed,discussion
44 | https://git.onem2m.org/issues/issues/-/issues/44 | Discussion: Proposal to remove table 6.2.2.2-1: oneM2M request parameters mapped as query-string field | Open |  | Andreas Kraft | TS-0009,discussion
45 | https://git.onem2m.org/issues/issues/-/issues/45 | TS-0001 and TS-0004: request/operationResult should not be mandatory | Open | no agreement yet | Miguel Angel Reina Ortega | TS-0001,TS-0004,fix needed
47 | https://git.onem2m.org/issues/issues/-/issues/47 | Software Campaign RSC value is ambiguous | Open | suggested improvement - needs new RSC | Bob Flynn | TS-0004
52 | https://git.onem2m.org/issues/issues/-/issues/52 | Software campaign create | Open |  | Bob Flynn | TS-0001
53 | https://git.onem2m.org/issues/issues/-/issues/53 | TS-0001: Description of stateTag in <contentInstance> | Open |  | Andreas Kraft | TS-0001
54 | https://git.onem2m.org/issues/issues/-/issues/54 | Software campaign ACPs | Open |  | Bob Flynn | TS-0001
55 | https://git.onem2m.org/issues/issues/-/issues/55 | software campaign cancelation procedure | Open | CR needed | Bob Flynn | TS-0001,TS-0004
56 | https://git.onem2m.org/issues/issues/-/issues/56 | TS-0004 <state> resource CREATE and UPDATE procedure | Open | CR needed | Poornima Shandilya | TS-0004,fix needed
57 | https://git.onem2m.org/issues/issues/-/issues/57 | Different Errors in TS-0004 when resource is not accessible | Open |  | Poornima Shandilya | TS-0004
60 | https://git.onem2m.org/issues/issues/-/issues/60 | Software Campaign managed resources | Open |  | Bob Flynn | TS-0001
61 | https://git.onem2m.org/issues/issues/-/issues/61 | Handling on failure of NIDD Configuration | Open | CRs SDS-2022-0185, SDS-2022-0186, SDS-2022-0187 | Poornima Shandilya | TS-0026
63 | https://git.onem2m.org/issues/issues/-/issues/63 | TS-0001 and TS-0004 contradicts on cancellation procedure of software operation | Open |  | Muhammad Hamza | TS-0001,TS-0004,discussion
65 | https://git.onem2m.org/issues/issues/-/issues/65 | TS-0004: incomplete Universal/Common attributes tables | Open | CR needed | Andreas Kraft | TS-0001
67 | https://git.onem2m.org/issues/issues/-/issues/67 | TS-0004 : Interpretations of mgmtDefinition missing in table Table 6.3.4.2.22-1 | Open |  | Andreas Kraft | TS-0004
68 | https://git.onem2m.org/issues/issues/-/issues/68 | TimeSeries: missingDataMaxNr not properly defined | Open |  | Andreas Kraft | TS-0001,TS-0004
69 | https://git.onem2m.org/issues/issues/-/issues/69 | TS-0004, TS-0001 : <action> is missing as a child resource in most resource definitions | Open | Relationship to 121? | Andreas Kraft | TS-0001,TS-0004,discussion
70 | https://git.onem2m.org/issues/issues/-/issues/70 | Conflicting descriptions for NotificationEventType E and expirationTime attribute | Open |  | Andreas Kraft | TS-0001,discussion
71 | https://git.onem2m.org/issues/issues/-/issues/71 | Procedures for rcn:12 (permissions) and its possible error(s) should be included in TS-0004 | Open |  | Muhammad Hamza | TS-0001,TS-0004,discussion
78 | https://git.onem2m.org/issues/issues/-/issues/78 | TS-0001: Inconsistencies in 9.6.26.3 - Common Attributes for Announced Resources | Open |  | Andreas Kraft | TS-0001,clarification needed
82 | https://git.onem2m.org/issues/issues/-/issues/82 | SDS : TS-0004 - Inconsistencies between Tables 6.3.4.2.1-1 (Interpretation of resourceType) and 6.3.4.2.11-1 (Interpretation of memberType) | Open |  | Andreas Kraft | TS-0004
84 | https://git.onem2m.org/issues/issues/-/issues/84 | TS-0004, TS-0001 : announceTo, announcedAttribute, link | Open |  | Andreas Kraft | TS-0001,TS-0004
85 | https://git.onem2m.org/issues/issues/-/issues/85 | TS-0004: Missing Interpretation of mgmtDefinition for OAuth2Authentifcation and wificlient | Open |  | Andreas Kraft | TS-0004
86 | https://git.onem2m.org/issues/issues/-/issues/86 | TS-0004: stateTag in <request> | Open |  | Andreas Kraft | SDS,TS-0004
87 | https://git.onem2m.org/issues/issues/-/issues/87 | Conditionally Mandatory and TS-0001 clause 9.6.26.3 | Open |  | Peter Niblett | TS-0001
91 | https://git.onem2m.org/issues/issues/-/issues/91 | TS-0004 : Procedure for UPDATE of <subscription>.notificationURI not mentioned | Open |  | Andreas Kraft | SDS,TS-0004
92 | https://git.onem2m.org/issues/issues/-/issues/92 | TS-0004 : handling of beaconRequester attribute is missing in procedures of 7.4.70.2.1 and 7.4.70.2.3 | Open |  | Andreas Kraft | SDS,TS-0004
93 | https://git.onem2m.org/issues/issues/-/issues/93 | Non-blocking asynchronous/synchronous in multihop scenario | Open |  | Miguel Angel Reina Ortega | SDS,TS-0001,TS-0004
98 | https://git.onem2m.org/issues/issues/-/issues/98 | Discussion: More than one timeSyncBeacon for Loss_of_Synchronization and same beaconRequester | Open |  | Andreas Kraft | SDS,TS-0001,discussion
99 | https://git.onem2m.org/issues/issues/-/issues/99 | TS-0001: Discrepancies in description of timeSyncBeacon's beaconInterval attribute | Open |  | Andreas Kraft | SDS,TS-0001
101 | https://git.onem2m.org/issues/issues/-/issues/101 | TS-0004: Missing XSD for m2m:timeSyncBeaconNotification | Open | XSD | Andreas Kraft | SDS,TS-0004,XSD
104 | https://git.onem2m.org/issues/issues/-/issues/104 | TS-0004: Missing short names for <group>'s somecastEnable and somecastAlgorithm attributes | Open |  | Andreas Kraft | SDS,TS-0004
105 | https://git.onem2m.org/issues/issues/-/issues/105 | Discussion: Is the prominent handling of stateTag necessary anymore | Open |  | Andreas Kraft | SDS,TS-0001,TS-0004,discussion
106 | https://git.onem2m.org/issues/issues/-/issues/106 | TS-0004: Typo in short name table (accessControlWindow) | Open |  | Andreas Kraft | SDS,TS-0004
107 | https://git.onem2m.org/issues/issues/-/issues/107 | SDS: missing short name for accessControlLocationRegions in TS-0004 | Open | Fixed in 4.12 | Andreas Kraft | SDS,TS-0004
108 | https://git.onem2m.org/issues/issues/-/issues/108 | SDS: Misspelled attribute name "deiveryAggregation" (should be "deliveryAggregation) | Open | Fixed in 4.12 | Andreas Kraft | SDS,TS-0004
111 | https://git.onem2m.org/issues/issues/-/issues/111 | Multiplicity of attributes in m2m:notification complex type | Open |  | Peter Niblett | TS-0004
112 | https://git.onem2m.org/issues/issues/-/issues/112 | TS-0001 clause 9.6.12 doesn't mention flexBlocking | Open |  | Peter Niblett | TS-0001,TS-0004
113 | https://git.onem2m.org/issues/issues/-/issues/113 | Need more precision on PollingChannel Request Aggregation | Open |  | Peter Niblett | TS-0004
114 | https://git.onem2m.org/issues/issues/-/issues/114 | XSDs missing for resources introduced in release 4 | Open | XSD | Poornima Shandilya | SDS,TS-0004,XSD
115 | https://git.onem2m.org/issues/issues/-/issues/115 | mappingThreshold attribute in ontologyMappingAlgorithm missing in TS-0001 v4.14.0 | Open |  | Miguel Angel Reina Ortega | SDS,TS-0001
116 | https://git.onem2m.org/issues/issues/-/issues/116 | Mismatching between TS-0001 and TS-0004 for some attribute datatypes in reasoningRules and reasoningJobInstance | Open | Fixed for v4 but not v3 | Miguel Angel Reina Ortega | SDS,TS-0001,TS-0004
119 | https://git.onem2m.org/issues/issues/-/issues/119 | Missing PrimitiveProfile and TimeSyncBeacon as child of CSEBase, AE and remoteCSE | Open |  | Miguel Angel Reina Ortega | SDS,TS-0001
120 | https://git.onem2m.org/issues/issues/-/issues/120 | Missing announceSyncType attribute in announcedResource in TS-0004 table 6.3.6-1 | Open |  | Miguel Angel Reina Ortega | SDS,TS-0004
121 | https://git.onem2m.org/issues/issues/-/issues/121 | Missing action resource as child of several resources | Open | CRs SDS-2022-0156, SDS-2022-0157 | Miguel Angel Reina Ortega | SDS,TS-0001,TS-0004
122 | https://git.onem2m.org/issues/issues/-/issues/122 | CSEBaseAnnc not implemented in XSD v3.22 | Open | XSD | Miguel Angel Reina Ortega | SDS,XSD
123 | https://git.onem2m.org/issues/issues/-/issues/123 | Unclear phrase in TS-0004 clause 7.2.1.2 | Open |  | Peter Niblett | SDS,TS-0004
125 | https://git.onem2m.org/issues/issues/-/issues/125 | Typo in CDT-mgmtCmd.xsd file for choice element | Open | XSD | Miguel Angel Reina Ortega | SDS,XSD
127 | https://git.onem2m.org/issues/issues/-/issues/127 | Content serialization in responses to forwarded requests | Open |  | Peter Niblett | SDS,TS-0004,discussion
128 | https://git.onem2m.org/issues/issues/-/issues/128 | Inconsistencies in Filter Criteria | Open | Fixed in 4.12 | Peter Niblett | SDS,TS-0004
129 | https://git.onem2m.org/issues/issues/-/issues/129 | Missing primitive specific operation for <fanOutPoint> | Open |  | Peter Niblett | SDS,TS-0004
132 | https://git.onem2m.org/issues/issues/-/issues/132 | Error in introduction to PollingChannel URI | Open | Fixed in 4.12 | Peter Niblett | SDS,TS-0004
136 | https://git.onem2m.org/issues/issues/-/issues/136 | TS-0001: Missing parent resource relationships in Table 9.6.1.1-1: Resource Types (for <crossResourceSubscription>) | Open |  | Andreas Kraft | SDS,TS-0001,editorial
137 | https://git.onem2m.org/issues/issues/-/issues/137 | TS-0004 : Missing namespace prefixes for enumerated types | Open | Fixed for v4 but not v3 | Andreas Kraft | SDS,TS-0004,editorial
140 | https://git.onem2m.org/issues/issues/-/issues/140 | TS-0001 : Typo in Table 10.2.7.10-1: <fanOutPoint> Subscribe | Open |  | Andreas Kraft | SDS,TS-0001,editorial
141 | https://git.onem2m.org/issues/issues/-/issues/141 | TS-0001: Missing parent resource relationships in Table 9.6.1.1-1: Resource Types (for <semanticDescriptor>) | Open |  | Andreas Kraft | SDS,TS-0001,editorial
142 | https://git.onem2m.org/issues/issues/-/issues/142 | TS-0004 : Non-normative language in 7.4.34.2.3 Originator: Update (SemanticDescriptor) | Open |  | Andreas Kraft | SDS,TS-0004,editorial
148 | https://git.onem2m.org/issues/issues/-/issues/148 | Which <mgmtCmd> types are cancellable? | Open | CR needed | Peter Niblett | SDS,TS-0004
150 | https://git.onem2m.org/issues/issues/-/issues/150 | Define behaviour for pending notifications when deleting a subscription | Open |  | Andreas Kraft | SDS,TS-0004
151 | https://git.onem2m.org/issues/issues/-/issues/151 | Inconsistency between TS-0004 clause 7.4.14.2.7 and TS-0026 (MBMS fanout) | Open |  | Peter Niblett | SDS,TS-0004,TS-0026
152 | https://git.onem2m.org/issues/issues/-/issues/152 | TS-0004 <execInstance> Cancel and Delete | Open |  | Peter Niblett | SDS,TS-0004
153 | https://git.onem2m.org/issues/issues/-/issues/153 | TS-0004 Issues with <SemanticFanOutPoint> | Open |  | Peter Niblett | SDS,TS-0004
154 | https://git.onem2m.org/issues/issues/-/issues/154 | Who creates and accesses <localMulticastGroup>s ? | Open |  | Peter Niblett | SDS,TS-0004
155 | https://git.onem2m.org/issues/issues/-/issues/155 | TS-0004 FlexContainer clarifications | Open |  | Peter Niblett | SDS,TS-0004
156 | https://git.onem2m.org/issues/issues/-/issues/156 | Unnecessary Note in TS-0004 clause 7.5.3.1.2 | Open |  | Peter Niblett | SDS,TS-0004
157 | https://git.onem2m.org/issues/issues/-/issues/157 | Relates to action item- A-SDS-42-01 primitive profile behavior for aggregated response | Open |  | Poornima Shandilya | SDS,TS-0004
158 | https://git.onem2m.org/issues/issues/-/issues/158 | Semantics : Discussion about query parameters | Open |  | Andreas Kraft | SDS,TS-0001,TS-0004
159 | https://git.onem2m.org/issues/issues/-/issues/159 | Need better examples in TS-0004 clause 7.3.3.17.0 | Open |  | Peter Niblett | SDS,TS-0004
160 | https://git.onem2m.org/issues/issues/-/issues/160 | Typo in TS-0004 6.3.4.2.11 | Open |  | Peter Niblett | SDS,TS-0004,editorial
161 | https://git.onem2m.org/issues/issues/-/issues/161 | TS-0001 : Wrong example for <serviceSubscribedAppRule>'s allowedApp-IDs attribute | Open |  | Andreas Kraft | SDS,TS-0001
162 | https://git.onem2m.org/issues/issues/-/issues/162 | TS-0009 : Clarification and correction for partial RETRIEVE | Open |  | Andreas Kraft | TS-0004,TS-0009
163 | https://git.onem2m.org/issues/issues/-/issues/163 | Inconsistent spelling of Trigger-Recipient-ID | Open |  | Peter Niblett | SDS,TS-0001,TS-0004
164 | https://git.onem2m.org/issues/issues/-/issues/164 | Issue in identifier formats and rule of use | Open |  | Poornima Shandilya
166 | https://git.onem2m.org/issues/issues/-/issues/166 | TS-0003- Missing step in AE impersonation procedure for registration request | Open |  | Poornima Shandilya
167 | https://git.onem2m.org/issues/issues/-/issues/167 | TS-0009: Possibly wrong presence of attributeList in CONTENT | Open |  | Andreas Kraft | SDS,TS-0009
168 | https://git.onem2m.org/issues/issues/-/issues/168 | Confusing instructions in TS-0004 clause 7.5.3.2 | Open |  | Peter Niblett
169 | https://git.onem2m.org/issues/issues/-/issues/169 | No resource-specific procedures for TimeSeries update | Open |  | Peter Niblett | TS-0004
170 | https://git.onem2m.org/issues/issues/-/issues/170 | Spelling of "Common Services Entity" in TS-0001 and TS-0004 | Open |  | Andreas Kraft | SDS,TS-0001,TS-0004,editorial
171 | https://git.onem2m.org/issues/issues/-/issues/171 | TS-0001 and TS-0004 have different wording in <pollingChannelURI> procedures | Open |  | Peter Niblett

## Baselines
SHORT DOC NB | SHORTNAME | SOURCE |  | STATUS
SDS-2022-0202 | TS-0001_v5_0_0_Baseline | Orange (Marianne) | 2022-11-30 | Agreed
SDS-2022-0196 | TS-0001_v4_17_0_Baseline | Orange (Marianne) | 2022-11-29 | Agreed
SDS-2022-0195 | TS-0001_v3_30_0_Baseline | Orange (Marianne) | 2022-11-29 | Agreed
SDS-2022-0194 | TS-0001_v2_34_0_Baseline | Orange (Marianne) | 2022-11-29 | Agreed
SDS-2022-0166R02 | TS-0004 v4.12.0 baseline | TS-0004 rapporteur | 2022-11-29 | Agreed
SDS-2022-0172 | TS-0022 v4.4.0 baseline | C-DOT | 2022-11-07 | Agreed
SDS-2022-0171 | TS-0022 v3.2.0 baseline | C-DOT | 2022-11-07 | Agreed
SDS-2022-0170 | TS-0022 v2.6.0 baseline | C-DOT | 2022-11-07 | Agreed
SDS-2022-0207 | TS-0010 v4.0.0 baseline | TS-0010 rapporteur | 2022-12-01 | Draft
SDS-2022-0208 | TS-0020 v4.0.0 baseline | SDS Chair | 2022-12-01 | Draft
SDS-2022-0209 | TS-0030 v4.0.0 baseline | SDS Chair | 2022-12-01 | Draft