## Contribs
SHORT DOC NB | SHORTNAME | SOURCE | STATUS | DOC TYPE | Release | TS/TR
SDS-2023-0208 | TS-0001_operationResult_multiplicity_R4 | Miguel Angel Reina Ortega (ETSI) | Draft | Change | R4 | TS-0001 | R3 mirror has been agreed
SDS-2023-0209 | TS-0004_operationResult_handling_R4 | Miguel Angel Reina Ortega (ETSI) | Draft | Change | R4 | TS-0004 | R3 mirror has been agreed
SDS-2023-0235R02 | Discussion of NGSI-LD Examples based on Bob s scenarios | NEC | Draft |  |  |  | Revised
SDS-2024-0067 | ResourceSSP_newAttributes_R5 | CDOT | Draft | New Feature | R5 | TS-0001
SDS-2024-0068 | CommonDeleteProcedure_correction_R5 | CDOT | Noted | Change | R5 | TS-0001 | Revision expected
SDS-2024-0069 | CommonDeleteProcedure_correction_R4 | CDOT | Draft | Change | R4 | TS-0001
SDS-2024-0043 | Replace mermaid diagrams with images | Andreas Kraft (Exacta) | Noted |  | R5 | TS-0020 | Awaiting creation of R5 baseline
SDS-2024-0021 | Corrections for WS binding | Andreas Kraft (Exacta GSS), Bob Flynn (Exacta GSS), Miguel Ortega (ETSI) | Draft | Change | R4 | TS-0020 | Awaiting creation of R5 baseline
SDS-2023-0189 | TS-0004_not_existing_attribute_R4 | Miguel Angel Reina Ortega (ETSI) | Draft | Change | R4 | TS-0004 | Left open
SDS-2023-0231R01 | expirationTime_handling_CREATE_UPDATE | C-DOT | Draft | Change | R4 | TS-0004
SDS-2023-0143R02 | TS-0001: Add enableEventNotificationOriginator attribute to subscription resource type | Andreas Kraft (DT), Andreas Neubacher (DT), Miguel Angel Reina Ortega (ETSI) | Draft | New Feature | R5 | TS-0001 | Revised
SDS-2023-0096R02 | Set “creator” attribute to request originator in notifications (TS-0004) | Andreas Kraft (DT), Andreas Neubacher (DT), Miguel Angel Reina Ortega (ETSI) | Draft | Change | R5 | TS-0004 | Awaiting agreement of 0143
SDS-2023-0086R01 | New event evaluation mode for crossResourceSubscription – TS-0001 | Andreas Kraft (DT), Andreas Neubacher (DT), Bob Flynn (Exacta GSS) | Draft | New feature | R5 | TS-0001 | Revised
SDS-2023-0087R01 | New event evaluation mode for crossResourceSubscription – TS-0004 | Andreas Kraft (DT), Andreas Neubacher (DT), Bob Flynn (Exacta GSS) | Draft | New feature | R5 | TS-0004 | Revised
SDS-2022-0173R02 | CSEResourceIDInterfaceCorrection_R4 | C-DOT | Draft | Change | R4 | TS-0001 | Revised
SDS-2022-0177R01 | Referencing Subscriptions | DT, Orange, Exacta GSS, CDOT | Draft | Discussion |  |  | Revised
SDS-2022-0182 | expirationTimeHandilinginSSP | C-DOT | Draft | Change | R4 | TS-0001 | Not opened yet
SDS-2022-0189R03 | expirationTime_Create_Update_Handling_R4 | C-DOT | Draft | Change | R4 | TS-0004 | Revised
SDS-2023-0232 | Using git for contributing to oneM2M | Miguel Angel Reina Ortega (ETSI) | Draft | Discussion | R5 |  | To be discussed at a F2F
SDS-2023-0143R02 | TS-0001: Add enableEventNotificationOriginator attribute to subscription resource type | Andreas Kraft (DT), Andreas Neubacher (DT), Miguel Angel Reina Ortega (ETSI) | Draft | New Feature | R5 | TS-0001
SDS-2023-0220 | Issues with WebSocket Binding Specification – TS-0020 | Andreas Kraft (DT), Andreas Neubacher (DT), Bob Flynn (Exacta GSS), Miguel Ortega (ETSI) | Noted | Discussion |  | TS-0020
SDS-2023-0171R02 | solutions for ML dataset management | KETI | Draft | New Feature | R5 | TR-0071
SDS-2023-0135 | TS-0001 subsciption repeatedNotifications | SyncTechno Inc. | Draft | New Feature | R5 | TS-0001
SDS-2023-0099 | TS-0001 subscription location based notifications | SyncTechno Inc. | Draft | New Feature | R5 | TS-0001
SDS-2023-0100 | TS-0001 mqtt multicastCapability | SyncTechno Inc. | Draft | New Feature | R5 | TS-0001
SDS-2023-0103 | Discussion paper on new updateMethod attribute for flexContainer | SyncTechno Inc. | Draft | Discussion | R5
SDS-2023-0104 | TS-0001 flexContainer updateMethod attribute | SyncTechno Inc. | Draft | New Feature | R5 | TS-0001
SDS-2023-0102R02 | TS-0001 Priority request primitive | SyncTechno Inc. | Draft | New Feature | R5 | TS-0001
SDS-2023-0203R02 | TS-0004 Priority request primitive | SyncTechno Inc. | Draft | New Feature | R5 | TS-0004
SDS-2023-0218 | TS-0022 new attributes for Registration | SyncTechno Inc. | Draft | Change | R5 | TS-0022
SDS-2023-0195 | TS-0001_new_announce_acpi_attribute_R5 | Miguel Angel Reina Ortega (ETSI), Andreas Kraft (DT), Bob Flynn (Exacta) | Draft | New Feature | R5 | TS-0001
SDS-2023-0033R07 | clarification of the behavior of flexContainerInstance in TS-0004 | Sejong University | Noted | Change | R4 | TS-0004 | Revision expected
SDS-2023-0179 | TS-0010 response topic clarification for MQTT URI targets | SyncTechno Inc. | Noted | Change | R4 | TS-0010 | Revision expected
SDS-2023-0105 | use cases of No-response option - CoAP | Abhijan Bhattacharyya, TCS | Noted | New Feature | R5 | TS-0008
SDS-2022-0020 | Discussion_on_announcement_issues | Deutsche Telekom, ETSI | Draft | New feature | R5 | TS-0001
SDS-2023-0125 | TS-0004_AnnouncementClarifications_R4 | Miguel Angel Reina Ortega (ETSI), Andreas Kraft (DT), Bob Flynn (Exacta) | Draft | Change | R4 | TS-0004
SDS-2023-0022R01 | TS-0004_XSD_rules_R4 | Miguel Angel Reina Ortega (ETSI), Andreas Kraft (DT) | Draft | Change | R4 | TS-0004 | Revised
SDS-2023-0028 | TS-0022_XSD_namespaces_R4 | Miguel Angel Reina Ortega (ETSI), Andreas Kraft (DT) | Draft | Change | R4 | TS-0022 | Not opened yet
SDS-2023-0079 | TS-0008 Introduce no-response option | Abhijan Bhattacharyya, TCS | Noted | Change | R5 | TS-0008 | Additional CRs expected
SDS-2022-0174 | CSEResourceIDInterfaceCorrection_R3 | C-DOT | Draft | Change | R3 | TS-0001 | Revision expected
SDS-2022-0175 | CSEResourceIDInterfaceCorrection_R2 | C-DOT | Draft | Change | R2 | TS-0001 | Revision expected
SDS-2022-0183R01 | TS-0001 - Another correction for the notificationStatsInfo and notificationStatsEnable | Andreas Kraft, Andreas Neubacher (Deutsche Telekom), Miguel Angel Reina Ortega (ETSI) | Draft | Change | R4 | TS-0001 | Revision expected
SDS-2022-0184R01 | TS-0004 - Another correction for the notificationStatsInfo and notificationStatsEnable attributes | Andreas Kraft, Andreas Neubacher (Deutsche Telekom), Miguel Angel Reina Ortega (ETSI) | Draft | Change | R4 | TS-0004 | Revision expected
SDS-2022-0190 | TS-0004_notificationContentType_R4 | Miguel Angel Reina Ortega (ETSI), Andreas Kraft (DT) | Noted | Change | R4 | TS-0004 | To be revisited
SDS-2022-0204 | Adding time retrieval method for constrained devices | Andreas Kraft, Andreas Neubacher (DT), Miguel Angel Reina Ortega (ETSI), Bob Flynn (Exacta GSS) | Draft | Change | R5 | TS-0001
SDS-2022-0205 | Access Control for Subscription Notifications | Andreas Kraft, Andreas Neubacher (DT), Miguel Angel Reina Ortega (ETSI), Bob Flynn (Exacta GSS) | Draft | Change |  | TS-0001
SDS-2022-0206 | fcinEnabled attribute to control flexContainerInstance R5 | Sejong Univ., Deutsche Telekom, Exactagss, Orange, EGM | Draft | Change | R5 | TS-0001
SDS-2022-0014R02 | Improving Queries in Discovery and Retrieve Requests | Deutsche Telekom | Noted | Discussion | R5 | TS-0001
SDS-2022-0110R04 | Automatic_recognition_of_identification_schemes_for_heterogeneous_IoT_identifiers | CMCC | Noted | New feature | R5 | TR-0033
SDS-2022-0124 | subjectAltName_AuthenticationProfile | C-DOT | Noted | Change | R4 | TS-0022 | Revision expected
SDS-2022-0143R02 | TS-0001 mlDatasetPolicy resource | KETI | Draft | New feature | R5 | TS-0001
SDS-2022-0144 | TS-0004 mlDatasetPolicy procedures | keti | Draft | New feature | R5 | TS-0004
SDS-2022-0149 | Enhancing [dataCollection] mgmtObj Specialization | Deutsche Telekom, C-DOT,Exactagss, Orange | Draft | Change | R5 | TS-0022
SDS-2022-0075 | Triggering Value Retrieval and Updates | Andreas Kraft, Andreas Neubacher (Deutsche Telekom), Bob Flynn (Exacta), Cyrille Bareau (Orange), Miguel Angel Reina Ortega (ETSI) | Draft | Discussion
SDS-2022-0015 | Add lastSeenTime and lastCommunicationTime attributes to <node> | Deutsche Telekom | Draft | New feature | R5 | TS-0001
ITU-T related
TP-2022-0032 | Updated Resolution table | Rana Kamill, BT | Noted | Notes | R2 | TS-0003
SDS-2022-0033 | Rel 2 Ref updates 1-TS-0003 | BT | Noted | Change | R2 | TS-0003 | May need revision - depends on ITU-T meeting
SDS-2022-0115R02 | Key_Storage | Rana Kamill, BT | Noted | Change | R2 | TS-0003 | Revision expected after Itu-T meeting
Other docs
SDS-2022-0002R01 | CMDH_Buffering | Exacta | Draft | Discussion | R5 | TS-0022 | Revised
SDS-2022-0008 | Improve TS-0001 clause 9.6.26.3 “Common Attributes for Announced Resources” | Deutsche Telekom | Noted | Change | R4 | TS-0001
SDS-2022-0036 | Introduction of new data types for Advanced Semantic Discovery | JK Consulting and Projects | Noted | New feature | R5 | TS-0004 | Revision expected
SDS-2022-0055 | Introduction_of_new_request_parameters_for_Advanced_Semantic_Discovery | JK Consulting and Projects | Noted | New feature | R5 | TS-0001 | Revision expected
SDS-2021-0259 | Key issue on Right to be Forgotten | Hyundai Motors, KETI | Draft | New feature | R5 | TR-0062
SDS-2021-0262R01 | gsma_reqts_001 | Exacta | Draft | New feature | R5 | TR-0063 | Not discussed
Agreed
Discussed
Needs Attention
Note on A95: Karen Hughes: Not discussed during SDS 52

## CR Packs
TS-0001 (R2) | TS-0001 (R3) | TS-0001 (R4) | TS-0001 (R5) | TS-0003 (R2) | TS-0003 (R3) | TS-0003 (R4) | TS-0004 (R2) | TS-0004 (R3) | TS-0004 (R4) | TS-0004 (R5) | TS-0005(R3) | TS-0006(R3) | TS-0008 (R2) | TS-0008 (R3) | TS-0008 (R4) | TS-0008 (R5) | TS-0009 (R2) | TS-0009 (R3) | TS-0009 (R4) | TS-0010 (R2) | TS-0010 (R3) | TS-0010 (R4) | TS-0014 (R2) | TS-0014 (R3) | TS-0022 (R2) | TS-0022 (R3) | TS-0022 (R4) | TS-0022 (R5) | TS-0026 (R3) | TS-0026 (R4) | TS-0026 (R5) | TS-0032 (R2) | TS-0032 (R3) | TS-0033 (R5) | TS-0034 (R5) | TS-0041 (R5)
[10 empty] | SDS-2021-0114R01 | [16 empty] | SDS-2024-0070 |  |  |  | SDS-2022-0185R04 |  |  | SDS-2022-0114R06 | SDS-2021-0217R03
SDS-2021-0190
SDS-2022-0006R01
SDS-2022-0062R02
SDS-2023-0064R01
SDS-2022-0186R04
SDS-2023-0130R01

## WI
WI | Title of WI | SDS39 | SDS40 | SDS41 | SDS42 | SDS43 | SDS44 | SDS45 | SDS46 | SDS47 | SDS48 | SDS49 | SDS50 | SDS51 | SDS52 | SDS53 | SDS54 | SDS55 | SDS56 | SDS57 | SDS58 | SDS59 | SDS60 | SDS61 | SDS62 | SDS63 | SDS64 | Comments
WI-0053 | Enhancements on Semantic Support | 30% | 40% | 50% | 75% | 90% | 95% | 97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0058 | Interworking with 3GPP networks | 60% | 68% | 75% | 80% | 80% | 90% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0072 | Modbus Interworking | 60% | 70% | 75% | 80% | 85% | 90% | 91% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0076 | Lightweight oneM2M Services | 20% | 40% | 50% | 60% | 65% | 70% | 80% | 85% | 90% | 93% | 97% | 97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0077 | Attribute based Access Control Policy | 65% | 75% | 75% | 80% | 85% | 85% | 90% | 92% | 93% | 95% | 97% | 97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0080 | Edge and Fog Computing | 20% | 35% | 45% | 55% | 65% | 70% | 80% | 85% | 90% | 95% | 97% | 97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0083 | oneM2M Service Subscribers and Users | 30% | 50% | 50% | 60% | 70% | 75% | 80% | 85% | 90% | 90% | 91% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0089 | Getting started with oneM2M | 20% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 25% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | R4/R5 work in progress
WI-0090 | oneM2M and Zigbee interworking | 0% | 0% | 0% | 0% | 0% | 30% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | Rel-5 TR work in progress
WI-0091 | oneM2M Services and Platform Discovery | 15% | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
WI-0095 | oneM2M System Enhancements to Support Data Protection Regulations | [5 empty] | 30% | 50% | 55% | 65% | 65% | 65% | 65% | 65% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | TR-0062 complete - No TS work yet
WI-0096 | Effective IoT Communication to Protect 3GPP Networks | [26 empty] | Bob has restarted it | bar: SDS39 to SDS64
WI-0100 | oneM2M and SensorThings API | [6 empty] | 5% | 5% | 15% | 20% | 20% | 20% | 25% | 25% | 40% | 50% | 50% | 50% | 55% | 70% | 70% | 70% | 75% | 75% | 77% | 77% | Rel-5 TS has started
WI-0101 | Advanced Semantic Discovery | SDS45: 5%; SDS46: 5%; SDS47: 15%; SDS56: 60%; SDS57: 60%; SDS58: 60%; SDS59: 60%; SDS60: 60%; SDS61: 60%; SDS62: 60%; SDS63: 60%; SDS64: 60% | TS started
WI-0102 | System enhancements to support Data License Management | [7 empty] | 5% | 15% | 30% | 40% | 45% | 45% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | Rel-5 TR work in progress
WI-0105 | System enhancements to support AI capabilities | SDS55: 75%; SDS56: 80%; SDS57: 85%; SDS58: 85%; SDS59: 85%; SDS60: 85%; SDS61: 85%; SDS62: 87%; SDS63: 87%; SDS64: 87% | Initial concepts discussed
WI-0109 | IPE-based_Device_Management_with_FlexContainers | 5% | 20% | 20% | 30% | 40% | 60% | 80% | 80% | 85% | 90% |  |  |  |  | 5% | 30% | 80% | 80% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | Rel 5 TS
WI-0112 | oneM2M Enhanced Filter and Queries | 5% | 20% | 20% | 30% | 40% | 60% | 80% | 80% | 85% | 90% | [10 empty] | 5% | 5% | 5% | 5% | 5% | 5% | Rel 5 TS
WI-0113 | Enhanced Public Warning Service Enabler | 5% | 20% | 20% | 30% | 40% | 60% | 80% | 80% | 85% | 90% | [10 empty] | 5% | 5% | 30% | 30% | 30% | 30% | Rel 5 TS
WI-0119 | Integrating_NGSI-LD_API_in_oneM2M | [26 empty] | Rel-5 TR work in progress | bar: SDS39 to SDS64
WI-0064 | Adaptation of oneM2M for Smart City | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
WI-0069 | Heterogen. identificat. service in oneM2M syst. | 50% | 50% | 60% | 60% | 60% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%