## Contribs
SHORT DOC NB | SHORTNAME | SOURCE | STATUS | DOC TYPE | Release | TS/TR
SDS-2025-0188 | MCP Architecture Overview | Ingo Friese DTAG | Not uploaded |  |  | TR-0081
SDS-2024-0021 | Corrections for WS binding | Andreas Kraft (Exacta GSS), Bob Flynn (Exacta GSS), Miguel Ortega (ETSI) | Not uploaded | Change | R4 | TS-0020
New and recently revised
SDS-2025-0191 | Updates on dataset resource type | KETI | Draft | New Feature | R5 | TR-0071
SDS-2025-0190 | Updates on model management interface | KETI | Draft | New Feature | R5 | TR-0071
SDS-2024-0089R02 | multiple_oldest_and_latest_instances_(TS-0004_R5) | KETI | Draft | New Feature | R5 | TS-0004 | Revised
SDS-2025-0189 | Default_Announcement_of_OA_Attributes | Bob Flynn (Exacta GSS) | Draft | Discussion
SDS-2025-0181R03 | Provide schemes for MQTT+WebSocket URIs | TS-0010 Rapporteur | Draft | Change | R4 | TS-0010
SDS-2025-0162 | Discussion on issue 236 - Delete | SDS Chair | Draft | Discussion
SDS-2025-0160 | adding geo-spatial functions | KETI | Draft | New Feature | R5 | TS-0004
SDS-2025-0057R01 | NGSI-LD to oneM2M Interworking Approach | NEC | Draft | New Feature | R5 | TR-0076 | Revised
SDS-2025-0059R02 | Service_Subscription_Determination_for_Resource | C-DOT | Draft | Discussion |  |  | Revised
SDS-2025-0187 | Security procedure for MCP Interworking | Jieun Lee, Jaehyung Jeong, JaeSeung Song (Sejong Univ.) | Noted | New Feature | R5 | TR-0081 | Revision expected
SDS-2025-0183 | Discoverability of Announced Resources | Andreas Kraft (Exacta) | Noted | Discussion | R5
SDS-2025-0133R03 | MCP_Introduction | Ingo Friese DTAG | Noted | New Feature | R5 | TR-0081 | Revised
SDS-2025-0161 | Discussion on updating an array element | KETI | Noted | Discussion
SDS-2025-0148R01 | SSP_Status_Checks_For_Targeted_Resource_R5 | CDOT | Agreed | Change | R5 | TS-0004
SDS-2025-0147R01 | SSP_Status_Checks_For_Targeted_Resource_R5 | CDOT | Agreed | Change | R5 | TS-0001
Other R4/R5 ready for review
SDS-2022-0177R01 | Referencing Subscriptions | DT, Orange, Exacta GSS, CDOT | Draft | Discussion |  |  | Revised
SDS-2024-0107 | ReferencingSubscription | C-DOT, EXACTAGSS | Draft | New Feature | R5 | TS-0001
SDS-2023-0220 | Issues with WebSocket Binding Specification – TS-0020 | Andreas Kraft (DT), Andreas Neubacher (DT), Bob Flynn (Exacta GSS), Miguel Ortega (ETSI) | Noted | Discussion |  | TS-0020 | Re-discuss
SDS-2022-0182 | expirationTimeHandilinginSSP | C-DOT | Draft | Change | R4 | TS-0001
SDS-2022-0173R02 | CSEResourceIDInterfaceCorrection_R4 | C-DOT | Draft | Change | R4 | TS-0001 | Revised
R4/R5 contributions being worked on
SDS-2025-0146 | New_Filter_Criteria_Parameter_SpecializationType_R5 | C-DOT | Noted | New Feature | R5 | TS-0004 | Revision expected
SDS-2025-0159R01 | ExpirationTime discussion | TS-0004 Rapporteur | Noted | Discussion |  |  | Discussion held - CRs needed
SDS-2025-0109 | TS-0004: Improve and clarify the flexContainerInstance behaviours | Andreas Kraft, Bob Flynn (Exacta GSS), JaeSeung Song, Seongjin Lee (Sejong University), Poornima Shandilya, Tapan Sethi (C-DOT), Cyrille Bareau (Orange) | Draft | Change | R4 | TS-0004 | Revision expected
SDS-2025-0110 | TS-0001: Improve and clarify the flexContainerInstance behaviours | Andreas Kraft, Bob Flynn (Exacta GSS), JaeSeung Song, Seongjin Lee (Sejong University), Poornima Shandilya, Tapan Sethi (C-DOT), Cyrille Bareau (Orange) | Draft | Change | R4 | TS-0001
SDS-2025-0121R03 | expirationTime_handling_CREATE_UPDATE_TS-0004_R5 | C-DOT | Draft | Change | R5 | TS-0004 | Revision expected
SDS-2023-0096R04 | Set “creator” attribute to request originator in notifications (TS-0004) | Andreas Kraft (DT), Andreas Neubacher (DT), Miguel Angel Reina Ortega (ETSI) | Noted | New Feature | R5 | TS-0004 | Revision expected
SDS-2025-0049 | geo-subscription interface | KETI | Noted |  | R5 | TS-0001 | Revision expected
SDS-2025-0056 | lastAccessTime Attribute of <AE> | Exacta GSS, C-DoT | Noted | New Feature | R5 | TS-0001 | Revision expected
SDS-2024-0129 | TR-0070-Enhanced filtering and Queries-v0_1_0_baseline | andreas | Draft | Baseline | R5 | TR-0070
SDS-2023-0105 | use cases of No-response option - CoAP | Abhijan Bhattacharyya, TCS | Noted | New Feature | R5 | TS-0008 | Discussion
SDS-2025-0019 | TS-0004: Allowing “noResponse” for all request procedures | Andreas Kraft (Exacta) | Noted | New Feature | R5 | TS-0004
SDS-2025-0020 | TS-0008: Supporting "noResponse" Response Type | Andreas Kraft (Exacta) | Noted | New Feature | R5 | TS-0008
SDS-2025-0021 | TS-0009: Supporting "noResponse" Response Type | Andreas Kraft (Exacta) | Draft | New Feature | R5 | TS-0009
SDS-2025-0022R01 | TS-0010: Supporting "noResponse" Response Type | Andreas Kraft (Exacta) | Draft | New Feature | R5 | TS-0010 | Revised
SDS-2024-0067R02 | ResourceSSP_newAttributes_R5 | CDOT | Noted | New Feature | R5 | TS-0001 | Revision expected
SDS-2025-0018 | ResourceSSP_newAttributes_R4 | CDOT | Draft | Change | R4 | TS-0001
SDS-2024-0081R01 | Correct the notificationEventType element’s description in m2m:notification | Andreas Kraft (Exacta GSS), Miguel Ortega (ETSI) | Draft | Change | R4 | TS-0004 | Revised
SDS-2025-0010R01 | TS-0001: notificationContentType for operationMonitor | Andreas Kraft (Exacta GSS), Poornima | Draft | Change | R5 | TS-0001 | Revised
SDS-2025-0011 | TS-0004: notificationContentType for operationMonitor | Andreas Kraft (Exacta GSS), Poornima | Noted | Change | R4 | TS-0004
SDS-2024-0119 | TS-0008 – Clarifications for request attribute encodings | Andreas Kraft (Exacta) | Noted | Change | R4 | TS-0008 | Revision expected
SDS-2023-0189 | TS-0004_not_existing_attribute_R4 | Miguel Angel Reina Ortega (ETSI) | Noted | Change | R4 | TS-0004 | Revision expected
Old ITU-T related contributions
TP-2022-0032 | Updated Resolution table | Rana Kamill, BT | Noted | Notes | R2 | TS-0003
SDS-2022-0033 | Rel 2 Ref updates 1-TS-0003 | BT | Noted | Change | R2 | TS-0003 | May need revision - depends on ITU-T meeting
SDS-2022-0115R02 | Key_Storage | Rana Kamill, BT | Noted | Change | R2 | TS-0003 | Revision expected after Itu-T meeting
Contributions deferred to R6
SDS-2022-0075R02 | Triggering Value Retrieval and Updates | Andreas Kraft, Andreas Neubacher (Deutsche Telekom), Bob Flynn (Exacta), Cyrille Bareau (Orange), Miguel Angel Reina Ortega (ETSI) | Draft | Discussion | R6 |  | Revised
SDS-2023-0086R01 | New event evaluation mode for crossResourceSubscription – TS-0001 | Andreas Kraft (DT), Andreas Neubacher (DT), Bob Flynn (Exacta GSS) | Draft | New feature | R6 | TS-0001 | Revised
SDS-2023-0087R01 | New event evaluation mode for crossResourceSubscription – TS-0004 | Andreas Kraft (DT), Andreas Neubacher (DT), Bob Flynn (Exacta GSS) | Draft | New feature | R6 | TS-0004 | Revised
Other Contributions
SDS-2023-0135 | TS-0001 subsciption repeatedNotifications | SyncTechno Inc. | Draft | New Feature | R5 | TS-0001
SDS-2023-0099 | TS-0001 subscription location based notifications | SyncTechno Inc. | Draft | New Feature | R5 | TS-0001
SDS-2023-0100 | TS-0001 mqtt multicastCapability | SyncTechno Inc. | Draft | New Feature | R5 | TS-0001
SDS-2023-0103 | Discussion paper on new updateMethod attribute for flexContainer | SyncTechno Inc. | Draft | Discussion | R5
SDS-2023-0104 | TS-0001 flexContainer updateMethod attribute | SyncTechno Inc. | Draft | New Feature | R5 | TS-0001
SDS-2023-0102R02 | TS-0001 Priority request primitive | SyncTechno Inc. | Draft | New Feature | R5 | TS-0001
SDS-2023-0203R02 | TS-0004 Priority request primitive | SyncTechno Inc. | Draft | New Feature | R5 | TS-0004
SDS-2023-0179 | TS-0010 response topic clarification for MQTT URI targets | SyncTechno Inc. | Noted | Change | R4 | TS-0010 | Revision expected
SDS-2023-0195 | TS-0001_new_announce_acpi_attribute_R5 | Miguel Angel Reina Ortega (ETSI), Andreas Kraft (DT), Bob Flynn (Exacta) | Draft | New Feature | R5 | TS-0001
SDS-2022-0020 | Discussion_on_announcement_issues | Deutsche Telekom, ETSI | Draft | New feature | R5 | TS-0001
SDS-2023-0125 | TS-0004_AnnouncementClarifications_R4 | Miguel Angel Reina Ortega (ETSI), Andreas Kraft (DT), Bob Flynn (Exacta) | Draft | Change | R4 | TS-0004
SDS-2022-0174 | CSEResourceIDInterfaceCorrection_R3 | C-DOT | Draft | Change | R3 | TS-0001 | Revision expected
SDS-2022-0175 | CSEResourceIDInterfaceCorrection_R2 | C-DOT | Draft | Change | R2 | TS-0001 | Revision expected
SDS-2022-0190 | TS-0004_notificationContentType_R4 | Miguel Angel Reina Ortega (ETSI), Andreas Kraft (DT) | Draft | Change | R4 | TS-0004 | To be revisited
SDS-2022-0204 | Adding time retrieval method for constrained devices | Andreas Kraft, Andreas Neubacher (DT), Miguel Angel Reina Ortega (ETSI), Bob Flynn (Exacta GSS) | Draft | Change | R5 | TS-0001
SDS-2022-0205 | Access Control for Subscription Notifications | Andreas Kraft, Andreas Neubacher (DT), Miguel Angel Reina Ortega (ETSI), Bob Flynn (Exacta GSS) | Draft | New Feature | R5 | TS-0001 | Discussion
SDS-2022-0014R02 | Improving Queries in Discovery and Retrieve Requests | Deutsche Telekom | Noted | Discussion | R5 | TS-0001
SDS-2022-0110R04 | Automatic_recognition_of_identification_schemes_for_heterogeneous_IoT_identifiers | CMCC | Draft | New feature | R5 | TR-0044
SDS-2022-0124 | subjectAltName_AuthenticationProfile | C-DOT | Noted | Change | R4 | TS-0022 | Revision expected
SDS-2022-0143R02 | TS-0001 mlDatasetPolicy resource | KETI | Draft | New feature | R5 | TS-0001
SDS-2022-0144 | TS-0004 mlDatasetPolicy procedures | keti | Draft | New feature | R5 | TS-0004
SDS-2022-0149 | Enhancing [dataCollection] mgmtObj Specialization | Deutsche Telekom, C-DOT,Exactagss, Orange | Draft | Change | R5 | TS-0022
SDS-2022-0015 | Add lastSeenTime and lastCommunicationTime attributes to <node> | Deutsche Telekom | Draft | New feature | R5 | TS-0001
SDS-2022-0002R01 | CMDH_Buffering | Exacta | Draft | Discussion | R5 | TS-0022 | Revised
SDS-2022-0008 | Improve TS-0001 clause 9.6.26.3 “Common Attributes for Announced Resources” | Deutsche Telekom | Noted | Change | R4 | TS-0001
SDS-2022-0036 | Introduction of new data types for Advanced Semantic Discovery | JK Consulting and Projects | Noted | New feature | R5 | TS-0004 | Revision expected
SDS-2022-0055 | Introduction_of_new_request_parameters_for_Advanced_Semantic_Discovery | JK Consulting and Projects | Noted | New feature | R5 | TS-0001 | Revision expected
SDS-2021-0259 | Key issue on Right to be Forgotten | Hyundai Motors, KETI | Draft | New feature | R5 | TR-0062
SDS-2021-0262R01 | gsma_reqts_001 | Exacta | Draft | New feature | R5 | TR-0063 | Not discussed
Other docs
SDS-2023-0232 | Using git for contributing to oneM2M | Miguel Angel Reina Ortega (ETSI) | Draft | Discussion | R5 |  | To be discussed at a F2F
Note on A100: Karen Hughes: Not discussed during SDS 52

## CR Packs
TS-0001 (R2) | TS-0001 (R3) | TS-0001 (R4) | TS-0001 (R5) | TS-0003 (R2) | TS-0003 (R3) | TS-0003 (R4) | TS-0004 (R2) | TS-0004 (R3) | TS-0004 (R4) | TS-0004 (R5) | TS-0005(R3) | TS-0006(R3) | TS-0008 (R2) | TS-0008 (R3) | TS-0008 (R4) | TS-0008 (R5) | TS-0009 (R2) | TS-0009 (R3) | TS-0009 (R4) | TS-0009 (R5) | TS-0010 (R2) | TS-0010 (R3) | TS-0010 (R4) | TS-0014 (R2) | TS-0014 (R3) | TS-0022 (R2) | TS-0022 (R3) | TS-0022 (R4) | TS-0022 (R5) | TS-0026 (R3) | TS-0026 (R4) | TS-0026 (R5) | TS-0030 (R5) | TS-0032 (R2) | TS-0032 (R3) | TS-0033 (R5) | TS-0034 (R5) | TS-0041 (R5)
[32 empty] | SDS-2022-0185R04 |  |  |  |  | SDS-2021-0217R03

## WI
WI | Title of WI | SDS39 | SDS40 | SDS41 | SDS42 | SDS43 | SDS44 | SDS45 | SDS46 | SDS47 | SDS48 | SDS49 | SDS50 | SDS51 | SDS52 | SDS53 | SDS54 | SDS55 | SDS56 | SDS57 | SDS58 | SDS59 | SDS60 | SDS61 | SDS62 | SDS63 | SDS64 | SDS65 | SDS66 | SDS67 | SDS68 | SDS69 | SDS70 | SDS71 | Comments
WI-0053 | Enhancements on Semantic Support | 30% | 40% | 50% | 75% | 90% | 95% | 97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | R4 - Complete
WI-0058 | Interworking with 3GPP networks | 60% | 68% | 75% | 80% | 80% | 90% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | R4 - Complete
WI-0072 | Modbus Interworking | 60% | 70% | 75% | 80% | 85% | 90% | 91% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | R4 - Complete
WI-0076 | Lightweight oneM2M Services | 20% | 40% | 50% | 60% | 65% | 70% | 80% | 85% | 90% | 93% | 97% | 97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | R4 - Complete
WI-0077 | Attribute based Access Control Policy | 65% | 75% | 75% | 80% | 85% | 85% | 90% | 92% | 93% | 95% | 97% | 97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | R4 - Complete
WI-0080 | Edge and Fog Computing | 20% | 35% | 45% | 55% | 65% | 70% | 80% | 85% | 90% | 95% | 97% | 97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | R4 - Complete
WI-0083 | oneM2M Service Subscribers and Users | 30% | 50% | 50% | 60% | 70% | 75% | 80% | 85% | 90% | 90% | 91% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | R4 - Complete
TR Only
WI-0091 | oneM2M Services and Platform Discovery | 15% | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | TR-0059 work in progress, no SDS yet
WI-0095 | System Enhancements to Support Data Protection Regulations | [5 empty] | 30% | 50% | 55% | 65% | 65% | 65% | 65% | 65% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | TR-0062 complete - No SDS yet
WI-0064 | Adaptation of oneM2M for Smart City | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | Need more use cases - e.g. from India
WI-0069 | Heterogeneous identification service in oneM2M | 50% | 50% | 60% | 60% | 60% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | Just a TR. No TS contributions
WI-0105 | System enhancements to support AI capabilities | SDS55: 75%; SDS56: 80%; SDS57: 85%; SDS58: 85%; SDS59: 85%; SDS60: 85%; SDS61: 85%; SDS62: 87%; SDS63: 87%; SDS64: 87%; SDS65: 87%; SDS66: 87%; SDS67: 87%; SDS68: 87%; SDS69: 87%; SDS70: 90%; SDS71: 90% | TR-0071 is progressing
Release 5
WI-0100 | oneM2M and SensorThings API | [6 empty] | 5% | 5% | 15% | 20% | 20% | 20% | 25% | 25% | 40% | 50% | 50% | 50% | 55% | 70% | 70% | 70% | 75% | 75% | 77% | 77% | 77% | 85% | 88% | 90% | 95% | 100% | 100% | TR-0072 complete. TS-0041 complete
WI-0101 | Advanced Semantic Discovery | SDS45: 5%; SDS46: 5%; SDS47: 15%; SDS56: 60%; SDS57: 60%; SDS58: 60%; SDS59: 60%; SDS60: 60%; SDS61: 60%; SDS62: 60%; SDS63: 60%; SDS64: 60%; SDS65: 60%; SDS66: 60%; SDS67: 60%; SDS68: 60%; SDS69: 60%; SDS70: 60%; SDS71: 60% | Additions to TS-0034 not started
WI-0102 | System enhancements to support Data License Management | [7 empty] | 5% | 15% | 30% | 40% | 45% | 45% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | TR-0066 complete - No TS work yet
WI-0109 | IPE-based_Device_Management_with_FlexContainers | 5% | 20% | 20% | 30% | 40% | 60% | 80% | 80% | 85% | 90% |  |  |  |  | 5% | 30% | 80% | 80% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | TS-0023 updates in progress
WI-0112 | oneM2M Enhanced Filter and Queries | 5% | 20% | 20% | 30% | 40% | 60% | 80% | 80% | 85% | 90% | [10 empty] | 5% | 5% | 5% | 5% | 5% | 5% | 10% | 10% | 10% | 10% | 20% | 20% | 20% | TR-0070 has started
WI-0113 | Enhanced Public Warning Service Enabler | 5% | 20% | 20% | 30% | 40% | 60% | 80% | 80% | 85% | 90% | [10 empty] | 5% | 5% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | TS-0037 (RDM), no SDS yet
WI-0119 | Integrating NGSI-LD API in oneM2M | SDS64: 5%; SDS65: 10%; SDS66: 20%; SDS67: 30%; SDS68: 35%; SDS69: 45%; SDS70: 45%; SDS71: 45% | TR-0071 work in progress
Targetting Release 6
WI-0090 | oneM2M and Zigbee interworking | 0% | 0% | 0% | 0% | 0% | 30% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | TR-0064 work has started
WI-0096 | Effective IoT Communication to Protect 3GPP Networks | [33 empty] | TR-0063 | bar: SDS39 to SDS71
WI-0115 | 3GPP Interworking via NEF N33 API | SDS39: 5%; SDS40: 20%; SDS41: 20%; SDS42: 30%; SDS43: 40%; SDS44: 60%; SDS45: 80%; SDS46: 80%; SDS47: 85%; SDS48: 90%; SDS59: 5%; SDS64: 0%; SDS65: 0%; SDS66: 0%; SDS67: 0%; SDS68: 0%; SDS69: 0%; SDS70: 0%; SDS71: 0% | Work has not started
WI-0120 | Edge Deployment using ETSI MEC | SDS69: 0%; SDS70: 5%; SDS71: 15% | TR-077 has started
WI-0121 | oneM2M ROS interworking | SDS69: 5%; SDS70: 15%; SDS71: 15% | TR-0079 work in progress
WI-0122 | oneM2M and Model Context Protocol | SDS70: 0%; SDS71: 15% | TR-0081 started