## Coversheet
Administrative Document
oneM2M-ADM-0001-V-7.0.0
Working Title: oneM2M Work Programme
18 October 2013
Copyright Notification
No part may be reproduced except as authorized by written permission.
The copyright and the foregoing restriction extend to reproduction in all media.
© 2012 - 2013 oneM2M Partners. All rights reserved.
Contents
History of Change ………………………………………………………….……………..Register A
1. Scope ……………………………………………………………….……………………….Page 3
2. References …………………………………………………………………...………….Page 3
3. Definitions, Abreviations …………………………………………….…………….Page 3
3.1 Definitions ………………………………………………………………..…………….Page 3
3.2 Abbreviations ……………………………………………………………………..….Page 3
Work Programme Overview …….…………………………….……………….…..Register B
Charts ……………………:………………………………………………………...…….…..Register C
Form for updating planning …….……::……………………………………….…..Register D
Calculations of data ………………...……………….::………………………….…..Register E
Approved deliverables ………………..……………….………………::……….…..Register F
1 Scope
text
2 References
2.1 Normative References
3 Definitions, Abbriviations
3.1 Definitions
3.2 Abbreviations

## A-History of Change
History of Change
V0.0.0 | 2013-08-05 | First draft of new Work Programme Report
V0.1.0 | 2013-08-08 | Incorporation of Raporteur updates
V7.0.0 | 2013-10-18 | First draft of administrative perm document "oneM2M-ADM-0001-oneM2M_Work_Programme-V7_00_00"

## B-WP Overview
|  |  |  | one M2M Work Programme Status: | 2013-10-18 (closing of TP7)
Work Item number | Primary responsible | Doc Type | Doc number | Title | Rapporteur | Milestone dates | [6 empty] | Level of completeness
[6 empty] | Start | Change Control |  | Freeze |  | Approval
[7 empty] | Target | Forecast | Target | Forecast | Target | Forecast
[6 empty] | TP no. / date | TP no. / date | TP no. / date | TP no. / date | TP no. / date | TP no. / date | TP no. / date
WI0001 |  |  |  | oneM2M Requirements
| WG1 - REQ | TR | TR-0001(WG1) | oneM2M use case collection | Philip Jacobs, Cisco | 1 | 4 | 4 | 6 | 6 | 8 | 7 | 100%
[6 empty] | 2012-09-24 | 2013-04-15 | 2013-04-15 | 2013-08-05 | 2013-08-05 | 2013-12-09 | 2013-10-14
| WG1 - REQ | TR |  | Benefits of oneM2M technology | Phil Hawkes, Qualcomm | TP#1 | TP#2 | TP#2 | TP#2 | forwarded to SC MARCOM for further use
[6 empty] | 2012-09-24 | 2012-12-10 | 2012-12-10 | 2012-12-10
| WG1 - REQ | TS | TS-0002(WG1) | M2M Requirements | Yu Qi, Huawei | 2 | 6 | 6 | 6 | 6 | 8 | 7 | 100%
[6 empty] | 2012-12-10 | 2013-08-05 | 2013-08-05 | 2013-08-05 | 2013-08-05 | 2013-12-09 | 2013-10-14
WI0002 |  |  |  | oneM2M Architecture
| WG2 - ARC | TS | TS-0001(WG2) | oneM2M Functional Architecture | Rajesh Bhalla, ZTE George Foti, Ericsson | 3 | 8 | 8 | 8 | 9 | 10 | 10 | 55%
[6 empty] | 2013-01-23 | 2013-12-09 | 2013-12-09 | 2013-12-09 | 2014-02-17 | 2014-04-07 | 2014-04-07
WI0003 |  |  |  | Vocabulary, Roles and Focus Areas for oneM2M Technical Work
| WG1 - REQ | TR | TR-0004(WG1) | Definition and Acronyms | Roland Hechwartner, Deutsche Telekom | 2 | 3 | 4 | 11 | 11 | 12 | 12 | 40%
[6 empty] | 2012-12-10 | 2013-01-23 | 2013-04-15 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
| WG1 - REQ | TR | TR-0005(WG1) | Roles and Focus Areas | Josef Blanz, Qualcomm | 2 | 3 | 4 | 11 | 11 | 12 | 12 | 30%
[6 empty] | 2012-12-10 | 2013-01-23 | 2013-04-15 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
WI0004 |  |  |  | Study of Management Capability Enablement Technologies for Consideration by oneM2M
| WG5 -MAS | TR | TR-0006(WG5) | Study of Management Capability Enablement Technologies for consideration by oneM2M | Jiaxin (Jason) Yin, Huawei | 3 | 7 | 7 | 7 | 7 | 8 | 8 | 90%
[6 empty] | 2013-01-23 | 2013-10-14 | 2013-10-14 | 2013-10-14 | 2013-10-14 | 2013-12-09 | 2013-12-09
WI0005 |  |  |  | oneM2M Abstraction and Semantics Capability Enablement
| WG5 -MAS | TR | TR-0007(WG5) | Study of Abstraction and Semantics Enablements | Joerg Swetina, NEC | 3 | 11 | 11 | 11 | 11 | 12 | 12 | 40%
[6 empty] | 2013-01-23 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
WI0006 |  |  |  | oneM2M Device/Gateway Classification
| WG2 - ARC | TR | TR-0010(WG2) | oneM2M Device/Gateway Classification | Hongbeom Ahn, LG Infocomm | 8 | 10 | 10 | 11 | 11 | 12 | 12 | 0%
[6 empty] | 2013-12-09 | 2014-04-07 | 2014-04-07 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
WI0007 |  |  |  | OneM2M Security Preliminary Investigations
| WG4 - SEC | TR | TR-0008(WG4) | Analysis of security solutions for oneM2M system | Claus Dietze, Giesecke & Devrient | 5 | 9 | 9 | 9 | 9 | 10 | 10 | 60%
[6 empty] | 2013-06-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-04-07 | 2014-04-07
| WG4 - SEC | TS | TS-0003(WG4) | One M2M Security solutions | Claus Dietze, Giesecke & Devrient | 6 | 10 | 10 | 10 | 10 | 11 | 11 | 10%
[6 empty] | 2013-08-05 | 2014-04-07 | 2014-04-07 | 2014-04-07 | 2014-04-07 | 2014-06-09 | 2014-06-09
WI0008 |  |  |  | OneM2M Protocol Development
| WG3 - PRO | TR | TR-0009(WG3) | one M2M Protocol Analysis | Philip Jacobs, Cisco, Richard Brennan, Telxxis | 5 | 9 | 9 | 9 | 9 | 10 | 10 | 15%
[6 empty] | 2013-06-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-04-07 | 2014-04-07
WI0009 |  |  |  | Protocol Analysis
| WG3 - PRO | TS | TS-0004(WG3) | OneM2M Service Layer Protocol and API Specification | Shingo Fujimoto, Fujitsu | 5 | 11 | 11 | 11 | 11 | 12 | 12 | 20%
[6 empty] | 2013-06-17 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
WI0010 | NEW |  |  | Management enablement
| WG5 -MAS | TS | TS-0005(WG5) | Management enablement (OMA) | SeungKyu Park (LG Electronics), Jiaxin Yin (Huawei Technologies) | 8 | 11 | 11 | 11 | 11 | 12 | 12 | 0%
[6 empty] | 2013-12-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
| WG5 -MAS | TS | TS-0006(WG5) | Management enablement (BBF) | Timothy Carey (Alcatel-Lucent) | 8 | 11 | 11 | 11 | 11 | 12 | 12 | 0%
[6 empty] | 2013-12-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
Note on I7: achieved
Note on I9: achieved
Note on I11: achieved
Note on I23: achieved
Note on I25: achieved
Note on J19: Same as freezing 1st release of TS on requirements and architecture (probably TP #6)
Note on K7: achieved

## C-Charts
Release 1
TP#7

## D-Entry Form
| one M2M Work Programme Status: | 2013-10-18 (closing of TP7)
Doc ID | Title | Rapporteur | Milestone dates | [6 empty] | Level of completeness
|  |  | Start | Change Control |  | Freeze |  | Approval
|  |  |  | Target | Forecast | Target | Forecast | Target | Forecast
| WG1 - REQ |  | TP# | TP# | TP# | TP# | TP# | TP# | TP#
TR-0001(WG1) | oneM2M use case collection | Philip Jacobs, Cisco | 1 | 4 | 4 | 6 | 6 | 8 | 7 | 100%
TR-0004(WG1) | Definition and Acronyms | Roland Hechwartner, Deutsche Telekom | 2 | 3 | 4 | 11 | 11 | 12 | 12 | 40%
TR-0005(WG1) | Roles and Focus Areas | Josef Blanz, Qualcomm | 2 | 3 | 4 | 11 | 11 | 12 | 12 | 30%
TS-0002(WG1) | M2M Requirements | Yu Qi, Huawei | 2 | 6 | 6 | 6 | 6 | 8 | 7 | 100%
WG2 - ARC
TR-0010(WG2) | oneM2M Device/Gateway Classification | Hongbeom Ahn, LG Infocomm | 8 | 10 | 10 | 11 | 11 | 12 | 12 | 0%
TS-0001(WG2) | oneM2M Functional Architecture | Rajesh Bhalla, ZTE George Foti, Ericsson | 3 | 8 | 8 | 8 | 9 | 10 | 10 | 55%
WG3 - PRO
TR-0009(WG3) | one M2M Protocol Analysis | Philip Jacobs, Cisco, Richard Brennan, Telxxis | 5 | 9 | 9 | 9 | 9 | 10 | 10 | 15%
TS-0004(WG3) | OneM2M Service Layer Protocol and API Specification | Shingo Fujimoto, Fujitsu | 5 | 11 | 11 | 11 | 11 | 12 | 12 | 20%
WG4 - SEC
TR-0008(WG4) | Analysis of security solutions for oneM2M system | Claus Dietze, Giesecke & Devrient | 5 | 9 | 9 | 9 | 9 | 10 | 10 | 60%
TS-0003(WG4) | One M2M Security solutions | Claus Dietze, Giesecke & Devrient | 6 | 10 | 10 | 10 | 10 | 11 | 11 | 10%
WG5 - MAS
TR-0006(WG5) | Study of Management Capability Enablement Technologies for consideration by oneM2M | Jiaxin (Jason) Yin, Huawei | 3 | 7 | 7 | 7 | 7 | 8 | 8 | 90%
TR-0007(WG5) | Study of Abstraction and Semantics Enablements | Joerg Swetina, NEC | 3 | 11 | 11 | 11 | 11 | 12 | 12 | 40%
TS-0005(WG5) | Management enablement (OMA) | SeungKyu Park (LG Electronics), Jiaxin Yin (Huawei Technologies) | 8 | 11 | 11 | 11 | 11 | 12 | 12 | 0%
TS-0006(WG5) | Management enablement (BBF) | Timothy Carey (Alcatel-Lucent) | 8 | 11 | 11 | 11 | 11 | 12 | 12 | 0%
Note on D13: Drafting start after TS-0001 Change Control
Note on E23: The TR should be put under change control and frozen one meeting before the last TP meeting of the oneM2M release
Note on G23: The TR should be put under change control and frozen one meeting before the last TP meeting of the oneM2M release
Note on I23: The TR should be approved at the last TP meeting of the oneM2M release

## E-Calculations
Do not delete this block structure
TP meeting dates
TP#1 | 2012-09-24
TP#2 | 2012-12-10
TP#3 | 2013-01-23
TP#4 | 2013-04-15
TP#5 | 2013-06-17
TP#6 | 2013-08-05
TP#7 | 2013-10-14
TP#8 | 2013-12-09
TP#9 | 2014-02-17
TP#10 | 2014-04-07
TP#11 | 2014-06-09
TP#12 | 2014-07-28
TP#13 | 2014-09-22
TP#14 | 2014-11-10
TP#15 | 2015-01-19
TP#16 | 2015-03-16
TP#17 | 2015-05-18
TP#18 | 2015-07-20
TP#19 | 2015-09-07
TP#20 | 2015-11-16
Do not delete this block structure
The following table is the 1:1 copy of the Entry-Form, it converts TP numbers into date format (yyyy-mm-dd) and additionally (manually) stores level of completeness of the last 2 reportings
0 | one M2M Work Programme Status: | 2013-10-18 (closing of TP7) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Doc ID | Title | Rapporteur | Milestone dates | 0 | 0 | 0 | 0 | 0 | 0 | Level of completeness | Level of completeness (TP#n-1) | Level of completeness (TP#n-2)
0 | 0 | 0 | Start | Change Control | 0 | Freeze | 0 | Approval | 0 | 0
0 | 0 | 0 | 0 | Target | Forecast | Target | Forecast | Target | Forecast | 0
0 | WG1 - REQ | 0 | TP# | TP# | TP# | TP# | TP# | TP# | TP# | 0
TR-0001(WG1) | oneM2M use case collection | Philip Jacobs, Cisco | 2012-09-24 | 2013-04-15 | 2013-04-15 | 2013-08-05 | 2013-08-05 | 2013-12-09 | 2013-10-14 | 100% | 95% | 80%
TR-0004(WG1) | Definition and Acronyms | Roland Hechwartner, Deutsche Telekom | 2012-12-10 | 2013-01-23 | 2013-04-15 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 40% | 40% | 20%
TR-0005(WG1) | Roles and Focus Areas | Josef Blanz, Qualcomm | 2012-12-10 | 2013-01-23 | 2013-04-15 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 30% | 20% | 20%
TS-0002(WG1) | M2M Requirements | Yu Qi, Huawei | 2012-12-10 | 2013-08-05 | 2013-08-05 | 2013-08-05 | 2013-08-05 | 2013-12-09 | 2013-10-14 | 100% | 95% | 80%
0 | WG2 - ARC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
TR-0010(WG2) | oneM2M Device/Gateway Classification | Hongbeom Ahn, LG Infocomm | 2013-12-09 | 2014-04-07 | 2014-04-07 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 0% | 0% | 0%
TS-0001(WG2) | oneM2M Functional Architecture | Rajesh Bhalla, ZTE George Foti, Ericsson | 2013-01-23 | 2013-12-09 | 2013-12-09 | 2013-12-09 | 2014-02-17 | 2014-04-07 | 2014-04-07 | 55% | 40% | 20%
0 | WG3 - PRO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TR-0009(WG3) | one M2M Protocol Analysis | Philip Jacobs, Cisco, Richard Brennan, Telxxis | 2013-06-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-04-07 | 2014-04-07 | 15% | 20% | 0%
TS-0004(WG3) | OneM2M Service Layer Protocol and API Specification | Shingo Fujimoto, Fujitsu | 2013-06-17 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 20% | 20% | 0%
0 | WG4 - SEC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TR-0008(WG4) | Analysis of security solutions for oneM2M system | Claus Dietze, Giesecke & Devrient | 2013-06-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-04-07 | 2014-04-07 | 60% | 40% | 0%
TS-0003(WG4) | One M2M Security solutions | Claus Dietze, Giesecke & Devrient | 2013-08-05 | 2014-04-07 | 2014-04-07 | 2014-04-07 | 2014-04-07 | 2014-06-09 | 2014-06-09 | 10% | 0% | 0%
0 | WG5 - MAS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TR-0006(WG5) | Study of Management Capability Enablement Technologies for consideration by oneM2M | Jiaxin (Jason) Yin, Huawei | 2013-01-23 | 2013-10-14 | 2013-10-14 | 2013-10-14 | 2013-10-14 | 2013-12-09 | 2013-12-09 | 90% | 80% | 80%
TR-0007(WG5) | Study of Abstraction and Semantics Enablements | Joerg Swetina, NEC | 2013-01-23 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 40% | 20% | 20%
TS-0005(WG5) | Management enablement (OMA) | SeungKyu Park (LG Electronics), Jiaxin Yin (Huawei Technologies) | 2013-12-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 0% | 0% | 0%
TS-0006(WG5) | Management enablement (BBF) | Timothy Carey (Alcatel-Lucent) | 2013-12-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 0% | 0% | 0%
The following table prepares the Gant Chart and the chart for deliverable completeness based on the table above. It contains only formulars for calculation.
Doc ID | Title | Doc ID | Start | Drafting | Delay | Change Control | Delay | Freeze | Delay | Level of completeness (actual) | Level of completeness (TP#n-1) | Level of completeness (TP#n-2)
TR-0001(WG1) | oneM2M use case collection | TR-0001(WG1) | 2012-09-24 | 203 | 0 | 112 | 0 | 126 | 0 | 100% | 95% | 80%
TR-0004(WG1) | Definition and Acronyms | TR-0004(WG1) | 2012-12-10 | 44 | 82 | 420 | 0 | 49 | 0 | 40% | 40% | 20%
TR-0005(WG1) | Roles and Focus Areas | TR-0005(WG1) | 2012-12-10 | 44 | 82 | 420 | 0 | 49 | 0 | 30% | 20% | 20%
TS-0002(WG1) | M2M Requirements | TS-0002(WG1) | 2012-12-10 | 238 | 0 | 0 | 0 | 126 | 0 | 100% | 95% | 80%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TR-0010(WG2) | oneM2M Device/Gateway Classification | TR-0010(WG2) | 2013-12-09 | 119 | 0 | 63 | 0 | 49 | 0 | 0% | 0% | 0%
TS-0001(WG2) | oneM2M Functional Architecture | TS-0001(WG2) | 2013-01-23 | 320 | 0 | 0 | 70 | 49 | 0 | 55% | 40% | 20%
TR-0009(WG3) | one M2M Protocol Analysis | TR-0009(WG3) | 2013-06-17 | 245 | 0 | 0 | 0 | 49 | 0 | 15% | 20% | 0%
TS-0004(WG3) | OneM2M Service Layer Protocol and API Specification | TS-0004(WG3) | 2013-06-17 | 357 | 0 | 0 | 0 | 49 | 0 | 20% | 20% | 0%
TR-0008(WG4) | Analysis of security solutions for oneM2M system | TR-0008(WG4) | 2013-06-17 | 245 | 0 | 0 | 0 | 49 | 0 | 60% | 40% | 0%
TS-0003(WG4) | One M2M Security solutions | TS-0003(WG4) | 2013-08-05 | 245 | 0 | 0 | 0 | 63 | 0 | 10% | 0% | 0%
TR-0006(WG5) | Study of Management Capability Enablement Technologies for consideration by oneM2M | TR-0006(WG5) | 2013-01-23 | 264 | 0 | 0 | 0 | 56 | 0 | 90% | 80% | 80%
TR-0007(WG5) | Study of Abstraction and Semantics Enablements | TR-0007(WG5) | 2013-01-23 | 502 | 0 | 0 | 0 | 49 | 0 | 40% | 20% | 20%
TS-0005(WG5) | Management enablement (OMA) | TS-0005(WG5) | 2013-12-09 | 182 | 0 | 0 | 0 | 49 | 0 | 0% | 0% | 0%
TS-0006(WG5) | Management enablement (BBF) | TS-0006(WG5) | 2013-12-09 | 182 | 0 | 0 | 0 | 49 | 0 | 0% | 0% | 0%
Axis options
Minimum: 41160
Maximum: 42000
Main interval: 120
Assisting interval: 30

## F-Approved Deliverables
Name | Version | Work Item | TP approval date | Forwarded to SC for publication
oneM2M-TR-0002-Architecture_Analysis_Part_1 | V-0.2.0 | WI0002 | 2013-08-05 | 2013-10-14
oneM2M-TR-0003-Architecture_Analysis_Part_2 | V-0.5.0 | WI0002 | 2013-08-05 | 2013-10-14
oneM2M-TS-0002-Requirements | V0_6_2 | WI0001 | 2013-10-17
oneM2M-TR-0001-UseCase | V0_0_5 | WI0001 | 2013-10-17